## Product Backlog
Sprint
Priority | Item | Details | Initial Size Estimate | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Define a DSL for programming the bot logic | Define and implement bot logic | 75 | 60 | 50 | 44 | 27 | 12 | 0 | 0
Define a DSL for using the implemented solution
2 | Implement Telegram API methods | Implement essential methods | 50 | 50 | 20 | 15 | 15 | 15 | 15
Implement additional methods (Optional)
3 | Develop a system to work in polling mode |  | 15 | 15 | 4 | 0 | 0 | 0 | 0 | 0
4 | Define architecture | Define architectural design | 10 | 2 | 2 | 2 | 2 | 2 | 2
Define design detail
5 | Setup proper unit tests |  | 15 | 15 | 7 | 7 | 7 | 7 | 2
6 | Develop final report |  | 20 | 19 | 19 | 19 | 19 | 19 | 19
7 | Setup Environment | Project and repository creation and setup | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Gradle automation process |  | 10 | 8 | 8 | 8 | 8 | 6 | 1
9 | CI/CD Setup | Automate building and testing | 32 | 27 | 22 | 15 | 11 | 11 | 11
Define and automate semantic versioning and releases
10 | Define project requirements |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Domain Driven Design | Knowledge crunching | 25 | 5 | 5 | 5 | 5 | 5 | 5
Ubiqutous language
Bounded context
User stories
12 | Refactoring | Refactor and clean-up code | 25 | 25 | 25 | 20 | 16 | 6 | 6
13 | Develop a system to provide fake updates for testing | (Optional) | 5 | 5 | 5 | 5 | 5 | 5 | 5
14 | Define a DSL for interacting with the Telegram API | Define a DSL that works on our Telegram API methods implementation (Optional) | 15 | 15 | 15 | 15 | 15 | 11 | 11
15 | Create some bots to showcase the library |  | 5 | 5 | 5 | 5 | 3 | 2 | 2
16 | Release on Maven Central | (Optional) | 5 | 5 | 5 | 5 | 5 | 5 | 3
17 | Develop a system to work in webhook mode | (Optional) | 10 | 10 | 10 | 10 | 10 | 10 | 10

## 1st Sprint Backlog
Remaining
Product Backlog Item | Sprint Task | Volunteer | Initial Estimate of Effort | 1 | 2 | 3 | 4 | 5 | 6
Define architecture | Define architectural design | Group | 5 | 5 | 5 | 5 | 2 | 0 | 0
| Define design detail | Group | 5 | 5 | 5 | 5 | 2 | 0 | 0
Enviroment setup | Create project | Tumedei | 2 | 2 | 2 | 0 | 0 | 0 | 0
| Create repository | Rossi | 2 | 1 | 0 | 0 | 0 | 0 | 0
| Setup Intellij IDE | Group | 4 | 4 | 4 | 1 | 0 | 0 | 0
Gradle automation process | Create a first version of build.gradle.kts | Group | 1 | 1 | 0 | 0 | 0 | 0 | 0
CI/CD setup | Automate building and testing | Group | 8 | 5 | 2 | 0 | 0 | 0 | 0
Domain Driven Design | Knowledge crunching | Group | 7 | 3.5 | 3.5 | 0 | 0 | 0 | 0
| Ubiqutous language | Group | 7 | 3.5 | 3.5 | 0 | 0 | 0 | 0
| Bounded context | Group | 7 | 3.5 | 3.5 | 0 | 0 | 0 | 0
| User stories | Group | 7 | 3.5 | 3.5 | 0 | 0 | 0 | 0
Define project requirements | Business requirements | Group | 4 | 4 | 4 | 4 | 4 | 0 | 0
| User requirements | Group | 2 | 2 | 2 | 2 | 2 | 0 | 0
| Functional requirements | Group | 2 | 2 | 2 | 2 | 2 | 0 | 0
| Non-functional requirements | Group | 4 | 4 | 4 | 4 | 4 | 0 | 0
| Implementation requirements | Group | 4 | 4 | 4 | 4 | 4 | 0 | 0
Setup project documentation | Trello | Group | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Product and sprint backlog | Boschi, Rossi, Tumedei | 5 | 3 | 1 | 0 | 0 | 0 | 0
| Create report and add chapters, create README | Boschi, Rossi, Tumedei | 1 | 1 | 1 | 1 | 1 | 0 | 0

## 2nd Sprint Backlog
Remaining
Product Backlog Item | Sprint Task | Volunteer | Initial Estimate of Effort | 1 | 2 | 3 | 4 | 5 | 6
Implement essential Telegram API methods | Start Telegram API methods implementation | Rossi, Boschi | 20 | 16 | 12 | 8 | 5 | 5 | 5
Define and implement case classes for interested entities
Define and implement bot logic | Start bot logic implementation | Tumedei | 30 | 25 | 20 | 15 | 10 | 10 | 10
Develop a system to work in polling mode | Begin works on update fetching in polling mode | Tumedei | 10 | 10 | 10 | 10 | 8 | 6 | 4
| Convert update JSON to model object | Boschi | 5 | 5 | 0 | 0 | 0 | 0 | 0
Setup proper unit tests | Use a TDD methodology for the above activities | Group | 15 | 10 | 8 | 7 | 7 | 7 | 7
CI/CD Setup | Improve GitHub Actions matrix expansion | Group | 5 | 5 | 5 | 5 | 4 | 2 | 0

## 3rd Sprint Backlog
Remaining
Product Backlog Item | Sprint Task | Volunteer | Initial Estimate of Effort | 1 | 2 | 3 | 4 | 5 | 6
Implement essential Telegram API methods | Start Telegram API methods implementation | Rossi, Boschi | 5 | 5 | 0 | 0 | 0 | 0 | 0
Define and implement case classes for interested entities
Refactoring | Refactor and clean code for all API methods | Group | 5 | 5 | 5 | 5 | 3 | 0 | 0
Define and implement bot logic | Complete bot logic implementation | Tumedei | 10 | 8 | 6 | 4 | 4 | 4 | 4
Develop a system to work in polling mode | Complete update fetching system for polling mode | Tumedei | 4 | 4 | 4 | 4 | 0 | 0 | 0
Define and automate semantic versioning and releases | Define and automate semantic versioning and releases | Group | 5 | 5 | 5 | 5 | 5 | 5 | 5
CI/CD Setup | Split compilation from testing to improve performance | Group | 5 | 5 | 4 | 0 | 0 | 0 | 0
| Setup code formatter (Scalafmt) and corresponding Gradle plugin | Group | 2 | 2 | 2 | 2 | 2 | 2 | 0

## 4th Sprint Backlog
Remaining
Product Backlog Item | Sprint Task | Volunteer | Initial Estimate of Effort | 1 | 2 | 3 | 4 | 5 | 6
Define and implement bot logic | Complete bot logic implementation | Tumedei | 4 | 2 | 0 | 0 | 0 | 0 | 0
| Implement utility methods to simplify bot Trigger creation | Group | 3 | 3 | 3 | 0 | 0 | 0 | 0
Define a DSL for using the implemented solution | Define the DSL structure | Group | 5 | 5 | 5 | 0 | 0 | 0 | 0
| Implement Keyboard DSL | Group | 5 | 5 | 5 | 5 | 0 | 0 | 0
Refactoring | Refactor models package | Group | 4 | 4 | 2 | 0 | 0 | 0 | 0
Define and automate semantic versioning and releases | Define and automate semantic versioning and releases | Group | 5 | 4 | 2 | 1 | 1 | 1 | 1
Create some bots to showcase the library | Create a basic working bot | Group | 2 | 2 | 2 | 2 | 0 | 0 | 0

## 5th Sprint Backlog
Remaining
Product Backlog Item | Sprint Task | Volunteer | Initial Estimate of Effort | 1 | 2 | 3 | 4 | 5 | 6
Define a DSL for using the implemented solution | Implement reactions DSL | Group | 15 | 10 | 6 | 4 | 0 | 0 | 0
Define a DSL for interacting with the Telegram API | Implement a DSL way to send mesages | Group | 4 | 4 | 0 | 0 | 0 | 0 | 0
Gradle automation process | Add a compile dependency for Scalafmt | Rossi | 2 | 2 | 2 | 2 | 2 | 2 | 0
Refactoring | Refactor models package | Tumedei | 2 | 2 | 2 | 2 | 2 | 0 | 0
| Refactor bot reactions | Tumedei | 4 | 2 | 2 | 2 | 0 | 0 | 0
| Streamline DSL logic | Group | 4 | 2 | 2 | 2 | 0 | 0 | 0
Create some bots to showcase the library | Create an example bot that uses the implemented DSL | Pistocchi, Tumedei | 1 | 1 | 1 | 0 | 0 | 0 | 0

## 6th Sprint Backlog
Remaining
Product Backlog Item | Sprint Task | Volunteer | Initial Estimate of Effort | 1 | 2 | 3 | 4 | 5 | 6
Release on Maven Central | Setup automatic release on Maven Central | Rossi, Pistocchi | 5 | 5 | 3 | 3 | 3 | 3 | 3
Gradle automation process | Setup dependabot | Rossi | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Save build output as artifact if the workflow fails | Rossi | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Add coverage tool | Rossi, Tumedei | 1 | 1 | 1 | 1 | 1 | 0 | 0
Define a DSL for programming the bot logic | Implement scenes DSL | Group | 8 | 8 | 8 | 6 | 6 | 4 | 0
| Add the option to create triggers that match any message | Group | 4 | 4 | 4 | 4 | 0 | 0 | 0
Setup proper unit tests | Add more tests to cover all aspects of the system | Group | 5 | 5 | 5 | 3 | 2 | 2 | 2
| Refactor tests to avoid using the Telegram API | Tumedei | 2 | 2 | 0 | 0 | 0 | 0 | 0